KAELUS.AI · SHIELDREADY CMMC 2.0 Compliance Platform

PROJECT ROADMAP

& TOOLS REGISTRY

ShieldReady v1.0  ·  March 2026

| 8 Phases | 16 Weeks to Launch | 38 Tools & Libraries | $0 Launch Budget |
| --- | --- | --- | --- |

Prepared by Kaelus.ai  ·  Confidential & Proprietary  ·  March 2026

# Table of Contents

# 1. Project Overview

ShieldReady is a CMMC 2.0 Compliance Readiness Platform built under the Kaelus.ai brand. It helps U.S. defense contractors — and the 220,000+ companies in the Defense Industrial Base (DIB) — achieve and maintain compliance with NIST SP 800-171 Rev 2, calculate their SPRS score, and generate assessment-ready evidence packages. The product is positioned as the affordable, AI-powered alternative to $5,000+/year consultants.

## 1.1 Relationship to Existing Kaelus.ai Product

The existing Kaelus.ai product — the Compliance Firewall Agent — is an LLM request gateway that intercepts, classifies, and blocks sensitive outbound data to AI providers. ShieldReady is a complementary product in the same Kaelus.ai compliance ecosystem, addressing a different but related compliance problem: helping defence contractors prove they are following CMMC/NIST rules, rather than monitoring LLM usage. Both products share the same Next.js 14 + Supabase codebase and brand identity.

|  | Compliance Firewall Agent | ShieldReady (CMMC Platform) |
| --- | --- | --- |
| Target User | Enterprise IT/Security | Defense contractors (DIB) |
| Core Problem | Prevent data leaks via LLM prompts | CMMC certification readiness |
| Revenue Model | B2B SaaS per-seat | B2B SaaS per-org + reports |
| Shared Stack | Next.js 14, Supabase, Tailwind | Next.js 14, Supabase, Tailwind |
| Status | Built (MVP live) | To be built |

## 1.2 Strategic Goals

- Reach $480K–$1.2M ARR by Year 2

- Serve 80,000+ DIB companies facing CMMC Level 1 & Level 2 mandates

- Position Kaelus.ai as the all-in-one compliance platform for the defense sector

- Unlock SBIR grant funding ($50K–$275K Phase I) as secondary revenue

- Exit potential: $300K–$1M sale to larger GovTech/RegTech acquirer

# 2. Current Project Status Review

## 2.1 What Is Already Built

The following components of the Kaelus.ai codebase exist and can be reused or extended for ShieldReady:

| Component | Description | Reuse for ShieldReady |
| --- | --- | --- |
| Next.js 14 App Shell | Full app router, layouts, auth guards, error boundaries | Yes — extend existing app |
| Supabase Auth | @supabase/ssr, session management, protected routes | Yes — add org/tenant logic |
| Dashboard Shell | Sidebar nav, responsive layout, dark mode, user dropdown | Yes — add ShieldReady pages |
| Supabase Schema | 6 compliance tables with RLS, migrations, indexes | Partial — add NIST tables |
| Tailwind + shadcn/ui | Full design system, components, theming | Yes — fully reusable |
| Vercel Deployment | CI/CD pipeline, env vars, serverless functions | Yes — same project |
| HITL Workflow | Approval queue, notifications, audit trail | Partial — adapt for assessors |
| Seed Anchoring | SHA-256 hash chain for tamper-proof logs | Yes — use for evidence integrity |

## 2.2 What Needs to Be Built

- NIST SP 800-171 Rev 2: 110-control database with plain-English explanations, SPRS weights, and remediation guidance

- SPRS Score Calculator: real-time scoring engine (-203 to +110) with domain-by-domain breakdown

- Gap Analysis Engine: identifies failing controls and prioritises remediation by impact

- Evidence Upload & Management: per-control file upload, tagging, expiry tracking

- Report Generator: Word/PDF export of System Security Plan (SSP), Plan of Action & Milestones (POA&M), and SPRS Score Report

- AI Assistant (Claude-powered): plain-English remediation recommendations per control

- Multi-Tenant Org Management: org creation, user invites, role-based access (Admin, Assessor, Viewer)

- Stripe Integration: subscription billing for all four pricing tiers

- Onboarding Wizard: 5-step guided setup for new organizations

- Landing Page & Pricing Page: ShieldReady-branded marketing pages

# 3. Development Roadmap

The roadmap is structured into 8 phases spanning 16 weeks (4 months). Each phase has clear deliverables, acceptance criteria, and dependencies. The entire build assumes a single developer working part-time (~15-20 hours/week) with $0 upfront tooling cost.

| Phase | Weeks | Name | Key Deliverable | Status |
| --- | --- | --- | --- | --- |
| 1 | 1-2 | Foundation | NIST DB + project scaffold | Start Now |
| 2 | 3-4 | Core Assessment | SPRS Calculator + Gap Analysis | Pending |
| 3 | 5-6 | Report Engine | SSP / POA&M / SPRS PDF Export | Pending |
| 4 | 7-8 | User & Org Management | Multi-tenant auth + roles | Pending |
| 5 | 9-10 | AI Assistant | Claude-powered remediation | Pending |
| 6 | 11-12 | Payments | Stripe subscriptions live | Pending |
| 7 | 13-14 | Beta & Polish | 10 beta users onboarded | Pending |
| 8 | 15-16 | Launch | Product live, GTM executing | Pending |

## Phase 1 — Foundation (Weeks 1–2)

| Phase 1 | Foundation Weeks 1–2 · Est. 25 hrs | START NOW | 8 Tasks |
| --- | --- | --- | --- |

This phase sets the data and infrastructure foundation everything else depends on. It cannot be skipped.

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | Study NIST SP 800-171 Rev 2 Assessment Guide (NIST SP 800-171A) | 4h | Notes doc | Critical |
| 2 | Design Supabase schema for 110-control database | 3h | Migration SQL | Critical |
| 3 | Seed all 110 controls with plain-English explanations, SPRS values, domain tags | 8h | Seed JSON/SQL | Critical |
| 4 | Create remediation guidance for each control | 4h | Seed data | High |
| 5 | Create evidence requirement list per control | 2h | Seed data | High |
| 6 | Scaffold ShieldReady app directory in Next.js | 2h | app/shieldready/ | Critical |
| 7 | Create organisation and assessment tables in Supabase | 1h | Migration SQL | Critical |
| 8 | Validate all seed data against official CMMC control list | 1h | Verified DB | Critical |

## Phase 2 — Core Assessment Engine (Weeks 3–4)

| Phase 2 | Core Assessment Engine Weeks 3–4 · Est. 30 hrs | PENDING | 9 Tasks |
| --- | --- | --- | --- |

Build the central product feature: the SPRS score calculator and gap analysis dashboard. This is the primary value proposition customers pay for.

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | Build assessment questionnaire UI (110 questions, paginated by domain) | 8h | UI Component | Critical |
| 2 | Implement SPRS scoring engine (DoD formula: 110 - sum of failures) | 4h | Scoring API | Critical |
| 3 | Build real-time score dashboard (gauge chart, domain breakdown) | 5h | Dashboard Page | Critical |
| 4 | Gap analysis table: show failing controls sorted by SPRS impact | 4h | Gap View | High |
| 5 | Save assessment progress to Supabase (auto-save every 30s) | 3h | Persistence | High |
| 6 | Assessment history: view past assessments and score trend | 3h | History View | Medium |
| 7 | Domain filter and search within controls | 2h | UI Feature | Medium |
| 8 | Write API route: POST /api/assessment, GET /api/assessment/:id | 1h | API Routes | Critical |

## Phase 3 — Report Generation Engine (Weeks 5–6)

| Phase 3 | Report Generation Engine Weeks 5–6 · Est. 28 hrs | PENDING | 7 Tasks |
| --- | --- | --- | --- |

Generate the three official documents assessors and C3PAOs expect: System Security Plan (SSP), Plan of Action & Milestones (POA&M), and the SPRS Score Submission Report. These are the primary paid deliverables.

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | Build SSP generator using docx-js (system description, control responses) | 8h | SSP .docx | Critical |
| 2 | Build POA&M generator (failing controls, remediation plan, target dates) | 6h | POA&M .docx | Critical |
| 3 | Build SPRS Score Report (one-page PDF for DoD submission via PIEE) | 5h | SPRS .pdf | Critical |
| 4 | Evidence upload UI per control (drag/drop, file type validation, storage) | 4h | Upload Feature | High |
| 5 | Supabase Storage bucket for evidence files with RLS | 2h | Storage Config | High |
| 6 | Evidence expiry tracking and renewal reminders | 2h | Alert System | Medium |
| 7 | Download report buttons in dashboard | 1h | UI | Critical |

## Phase 4 — User & Org Management (Weeks 7–8)

| Phase 4 | User & Org Management Weeks 7–8 · Est. 22 hrs | PENDING | 6 Tasks |
| --- | --- | --- | --- |

Implement multi-tenant architecture so one organization can have multiple users with role-based access. This unlocks the Team and Enterprise tiers.

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | Organisation creation flow (name, CAGE code, DUNS/UEI number, contract type) | 4h | Org Setup | Critical |
| 2 | User invite system (email invite → Supabase magic link) | 4h | Invite Flow | High |
| 3 | Role-based access control: Admin, Compliance Manager, Assessor, Viewer | 4h | RBAC System | High |
| 4 | Supabase RLS policies scoped to org_id | 3h | DB Security | Critical |
| 5 | User management page (list, edit roles, remove users) | 4h | Settings Page | High |
| 6 | Onboarding wizard (5-step guided setup for new orgs) | 3h | Wizard UI | High |

## Phase 5 — AI Assistant (Weeks 9–10)

| Phase 5 | AI Remediation Assistant Weeks 9–10 · Est. 20 hrs | PENDING | 5 Tasks |
| --- | --- | --- | --- |

Integrate Claude (claude-sonnet-4-6) to provide plain-English remediation guidance for each failing control. This is the differentiator that justifies premium tier pricing.

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | Build AI chat panel in assessment view (context-aware per control) | 6h | AI Panel | High |
| 2 | Implement Claude API streaming response (real-time token output) | 3h | Streaming API | High |
| 3 | System prompt engineering: CMMC expert persona + control context injection | 3h | Prompt Template | Critical |
| 4 | AI-generated remediation plan export (append to POA&M) | 3h | Export Feature | Medium |
| 5 | Rate limiting and token cost tracking per org | 2h | Usage Tracking | Medium |
| 6 | AI usage gating by subscription tier (Starter: limited, Professional+: unlimited) | 3h | Tier Gating | High |

## Phase 6 — Payment Integration (Weeks 11–12)

| Phase 6 | Payments & Subscriptions Weeks 11–12 · Est. 18 hrs | PENDING | 6 Tasks |
| --- | --- | --- | --- |

Monetise the product with Stripe subscriptions. All four pricing tiers must be live with proper gating, billing portal access, and webhook handling.

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | Create Stripe products: Starter ($79), Professional ($149), Enterprise ($299), Consultant ($499) | 2h | Stripe Products | Critical |
| 2 | Implement Stripe Checkout session API route | 3h | Checkout Flow | Critical |
| 3 | Stripe webhook handler: subscription created, updated, cancelled | 4h | Webhook Handler | Critical |
| 4 | Subscription status stored in Supabase (org.subscription_tier) | 2h | DB Update | Critical |
| 5 | Feature gating by subscription tier across all pages | 4h | Gate System | High |
| 6 | Stripe Customer Portal integration (self-serve billing management) | 2h | Billing Portal | High |
| 7 | Pricing page with Stripe Checkout links | 1h | Pricing Page | High |

## Phase 7 — Beta Testing & Polish (Weeks 13–14)

| Phase 7 | Beta Testing & Polish Weeks 13–14 · Est. 20 hrs | PENDING | 6 Tasks |
| --- | --- | --- | --- |

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | Recruit 10 beta users from r/CMMC, LinkedIn, NDIA forums | 4h | 10 Beta Users | Critical |
| 2 | Set up feedback collection (Tally form embedded in app) | 1h | Feedback Form | High |
| 3 | Bug triage and critical fixes from beta feedback | 8h | Bug Fixes | Critical |
| 4 | Performance optimisation: lazy loading, query caching, image compression | 3h | Perf Gains | Medium |
| 5 | Mobile responsiveness audit and fixes | 2h | Mobile Ready | Medium |
| 6 | Accessibility (WCAG 2.1 AA) audit: contrast, keyboard nav, ARIA | 2h | A11y Pass | Medium |

## Phase 8 — Launch (Weeks 15–16)

| Phase 8 | Public Launch Weeks 15–16 · Est. 15 hrs | PENDING | 7 Tasks |
| --- | --- | --- | --- |

| # | Task | Est. Hours | Output | Priority |
| --- | --- | --- | --- | --- |
| 1 | SEO-optimised landing page (keyword: 'CMMC compliance software', 'SPRS calculator') | 4h | Landing Page | Critical |
| 2 | Post on r/CMMC, r/cybersecurity, LinkedIn, NDIA forum | 2h | GTM Posts | Critical |
| 3 | Product Hunt submission (prepare assets, launch day coordination) | 3h | PH Launch | High |
| 4 | Set up Resend transactional emails (welcome, weekly score digest) | 2h | Email Flows | High |
| 5 | Vercel Analytics + Sentry error monitoring live | 1h | Monitoring | High |
| 6 | Write SBIR Phase I proposal for DoD SBIR (next open solicitation) | 3h | Grant Proposal | Medium |

# 4. Key Milestones & Success Metrics

| Week | Phase End | Milestone | Success Metric |
| --- | --- | --- | --- |
| Week 2 | Phase 1 | NIST control DB seeded and schema live | 110 controls in Supabase, all with SPRS values |
| Week 4 | Phase 2 | SPRS Calculator functional | Score recalculates correctly for all 110 controls |
| Week 6 | Phase 3 | SSP + POA&M export working | Both documents download as valid .docx/.pdf |
| Week 8 | Phase 4 | Multi-tenant auth live | Two orgs can each see only their own data |
| Week 10 | Phase 5 | AI assistant live | Claude answers per-control questions accurately |
| Week 12 | Phase 6 | First paid subscriber | $79+ MRR from Stripe |
| Week 14 | Phase 7 | Beta complete | 10 beta users, NPS > 7 |
| Week 16 | Phase 8 | Public launch | 100 sign-ups, 10 paying customers |
| Month 6 | Post-launch | Revenue milestone | $10K MRR (approx. 67 Professional tier) |
| Month 12 | Year 1 | Product-market fit | $40K MRR / $480K ARR |

# 5. Complete Tools & Technologies Registry

This section lists every tool, library, service, and API required to build and operate ShieldReady. Each entry includes its role, cost tier, and which phase it is first introduced.

## 5.1 Frontend Framework & UI

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| Next.js 14 | Full-stack React framework | App Router, Server Components, API routes, ISR caching | Free | 1 |
| React 18 | UI rendering library | Concurrent rendering, Suspense, server actions | Free | 1 |
| TypeScript 5 | Type-safe JavaScript | Catches 60%+ of runtime bugs at compile time | Free | 1 |
| Tailwind CSS v3 | Utility-first CSS framework | Rapid styling, purges unused CSS, dark mode built-in | Free | 1 |
| shadcn/ui | Headless component library | Accessible, unstyled components built on Radix UI | Free | 1 |
| Radix UI Primitives | Accessible UI primitives | Underlying layer for shadcn/ui (Dialog, Select, Toast, etc.) | Free | 1 |
| Lucide React | Icon library | 600+ consistent SVG icons, tree-shakeable | Free | 1 |
| Recharts | Chart library for React | SPRS score gauge, domain bar charts, trend lines | Free | 2 |
| React Hook Form | Form state management | Performant forms with Zod schema validation | Free | 2 |
| Zod | Schema validation | Type-safe runtime validation for forms and APIs | Free | 1 |
| next-themes | Dark/light mode | Already in project, extend for ShieldReady | Free | 1 |

## 5.2 Backend, Database & Auth

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| Supabase (Free) | PostgreSQL DB + Auth + Storage | Free tier: 500MB DB, 2GB file storage, 50K MAU, unlimited API calls | Free* | 1 |
| @supabase/ssr | Next.js Auth integration | Cookie-based sessions, middleware auth guards, SSR-compatible | Free | 1 |
| @supabase/supabase-js | Supabase client SDK | Type-safe DB queries, realtime subscriptions, storage API | Free | 1 |
| Supabase Storage | Evidence file storage | Per-control file uploads with org-scoped RLS policies | Free* | 3 |
| Supabase Realtime | Live score updates | WebSocket-based real-time score dashboard updates | Free | 2 |
| PostgreSQL (via Supabase) | Relational database | NIST controls, assessments, orgs, users, evidence, scores | Free* | 1 |

* Free tier limits. Upgrade to Supabase Pro ($25/mo) when you exceed 500MB storage or 2GB file uploads.

## 5.3 AI & LLM Integration

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| Anthropic Claude API | AI remediation assistant | Model: claude-sonnet-4-6. Streaming responses for per-control guidance | Pay-per-use | 5 |
| @anthropic-ai/sdk | Claude Node.js SDK | Official SDK for chat completions, streaming, token counting | Free | 5 |
| AI SDK (Vercel) | Streaming UI helper | useChat() hook, streaming text rendering in React | Free | 5 |

Estimated Claude API cost: ~$0.003 per 1K tokens. A full 110-control assessment session ≈ $0.05. Budget: ~$20/month at 400 active users.

## 5.4 Document Generation

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| docx (docx-js) | Word document generation | SSP and POA&M as .docx. Already proven in PRD generation. | Free | 3 |
| pdf-lib | PDF generation | SPRS Score Report as PDF. Merge pages, add stamps, form fill. | Free | 3 |
| @react-pdf/renderer | React-to-PDF rendering | Alternative for complex multi-page PDF layouts in React | Free | 3 |

## 5.5 Payment Processing

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| Stripe | Subscription billing | Checkout, Customer Portal, webhooks. 2.9% + $0.30 per transaction. | 2.9%+$0.30 | 6 |
| stripe (Node SDK) | Server-side Stripe calls | Create checkout sessions, manage subscriptions, handle webhooks | Free | 6 |
| @stripe/stripe-js | Client-side Stripe | Stripe.js for PCI-compliant payment element embedding | Free | 6 |

## 5.6 Email & Notifications

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| Resend | Transactional email | Welcome email, weekly SPRS digest, evidence expiry alerts. Free: 3K/mo. | Free* | 8 |
| react-email | Email template builder | Build HTML emails as React components, preview in browser | Free | 8 |

## 5.7 Deployment & DevOps

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| Vercel (Hobby) | Hosting & CI/CD | Auto-deploy on git push, preview deployments, serverless functions. Free for hobby. | Free* | 1 |
| Git + GitHub | Version control | Source of truth for all code, branch protection, PR reviews | Free | 1 |
| Vercel Analytics | Traffic analytics | Page views, user sessions, performance metrics. Built into Vercel. | Free | 8 |
| Sentry | Error monitoring | Capture and alert on runtime errors, performance traces. Free: 5K errors/mo. | Free* | 8 |

* Upgrade Vercel to Pro ($20/mo) when you need custom domains and higher function limits. Upgrade on first paid customer.

## 5.8 Development Tools

| Tool | Purpose | Notes | Cost | Phase |
| --- | --- | --- | --- | --- |
| ESLint | Code linting | Catch errors and enforce code style. Already in project. | Free | 1 |
| Prettier | Code formatting | Auto-format on save. Consistent style across the codebase. | Free | 1 |
| Supabase CLI | Local DB development | Run Supabase locally, write and test migrations before pushing | Free | 1 |
| tsx | TypeScript execution | Run .ts scripts directly. Already used for WebSocket server. | Free | 1 |
| Playwright | End-to-end testing | Automated browser tests for critical flows (sign-up, assessment, payment) | Free | 7 |
| VS Code / Cursor | IDE | Recommended IDE. Cursor adds AI pair-programming on top of VS Code. | Free | 1 |

## 5.9 External APIs & Compliance Data Sources

| Source | Purpose | Access Method | Cost | Phase |
| --- | --- | --- | --- | --- |
| NIST SP 800-171 Rev 2 | 110 security control definitions | Public PDF download from csrc.nist.gov. Manually seed into DB. | Free | 1 |
| NIST SP 800-171A | Assessment procedures per control | Public PDF. Use to write evidence requirement descriptions. | Free | 1 |
| CMMC Assessment Guide | Examiner guidance for each control | Public download from dodcio.defense.gov | Free | 1 |
| DoD PIEE Portal | SPRS score submission endpoint | Link users to piee.eb.mil for official submission (no API) | Free | 3 |
| SAM.gov | Contractor registration verification | Verify UEI/CAGE codes via SAM.gov public search | Free | 4 |
| Tally.so | Beta feedback forms | Embed free survey forms in app for feedback collection | Free | 7 |

## 5.10 Total Cost Summary

ShieldReady can be built and operated at $0/month until first paid customer. The table below shows the cost at each growth stage.

| Service | At Launch (0 customers) | At $5K MRR (33 orgs) | At $40K MRR (267 orgs) |
| --- | --- | --- | --- |
| Vercel | $0 (Hobby) | $20/mo (Pro) | $20/mo (Pro) |
| Supabase | $0 (Free) | $0 (Free) | $25/mo (Pro) |
| Claude API | $0 | ~$5/mo | ~$40/mo |
| Stripe | $0 | 2.9%+$0.30/txn | 2.9%+$0.30/txn |
| Resend | $0 (Free 3K/mo) | $0 (Free) | $20/mo (paid) |
| Sentry | $0 (Free 5K) | $0 (Free) | $26/mo (paid) |
| Domain (Namecheap) | ~$12/yr | — | — |
| TOTAL MONTHLY | ~$1/mo | ~$25–35/mo | ~$131/mo |

# 6. Immediate Action Items — Start Today

The following tasks should be completed this week to begin Phase 1. They are ordered by dependency — complete them in sequence.

| # | Action | Resource | Est. Time |
| --- | --- | --- | --- |
| 1 | Download NIST SP 800-171 Rev 2 PDF from csrc.nist.gov | csrc.nist.gov/publications/detail/sp/800-171/rev-2/final | 15 min |
| 2 | Download CMMC Assessment Guide from dodcio.defense.gov | dodcio.defense.gov/CMMC/Documentation/ | 15 min |
| 3 | Create Supabase migration: nist_controls, assessments, orgs tables | Supabase SQL Editor | 2 hrs |
| 4 | Seed the 110 NIST controls (ID, domain, title, description, SPRS value) | Node seed script | 4 hrs |
| 5 | Create app/shieldready/ directory in Next.js project | VS Code / Cursor | 30 min |
| 6 | Create dashboard/shieldready/page.tsx — stub page to verify routing | VS Code / Cursor | 30 min |
| 7 | Create Anthropic account and get API key for Phase 5 | console.anthropic.com | 15 min |
| 8 | Create Stripe account (test mode) and note publishable + secret keys | dashboard.stripe.com | 15 min |

Once these 8 tasks are done, you will have: the NIST database seeded, the app scaffold in place, and all third-party accounts registered. That is the complete foundation for Phase 1.

Remember: Every week you delay is a week a competitor could fill the CMMC compliance gap. The mandate is real, the market is underserved, and the stack is already built. The only thing left is execution. Build. Ship. Iterate. Let's go.